S-ISA-64 Project Roadmap and Plans

---
Project End Goals
1. Glorify Jesus of Nazareth in all of this (Most important)
2. Fast virtual machine. Able to be used as a suitable
Replacement for the host CPU. Self-hosting high level
Language compiler, preferably C, should be available.
3. Hardware implementation. Silicon that implements
The S-ISA-64 architecture should exist.
4. Public domain. No attribution requirements or licensing issues.
5. Disk operating system with multitasking and multithreading
Running on the architecture.
6. Hardware simulator. A sub-cycle accurate simulator should exist
For the hardware implementation for debugging and testing.
7. Standard for connecting peripherals and whatnot.

---
Project Phases
Phase 1: ISA and language development.
- Get a working macro-assembler and linker (mostly finished)
- Standardize the instruction set (Almost finished)
- Determine the ABI
- Write developer documentation for instruction set.
- Publish work on Github
- Get interest from other developers (if possible)
Phase 2: Operating System testbench development
- Get a basic operating system running (similar to KRENEL)	- boot user mode programs and service system calls
- Only need a round robin scheduler
- Probably going to write it all in assembly language.
- This phase will start to standardize peripheral (device) access.
- Get interested developers
Phase 3: Compiler development
- Retargeting LCC?
- Retargeting Small-C?
- Need to do significant rewriting to support types properly.
- Write my own language?
- I already have a lot of work done in this area.
- Write an LLVM backend?
- Just make the assembler more advanced?
- Get a team
Phase 4: Hardware simulation
- Begin designing hardware layout
- Hopefully have hardware engineers to consult/work with at this phase.
- Design the physical components in software
- Re-work existing technology to better suit hardware limitations.
Phase 5: Hardware Implementation
- If the project ever reaches this phase, there should be a team of developers available to work part-time or full-time.
- Too far into the future to plan

---
Why is it useful?
1. Simpler to write code for
2. Public domain
3. (hopefully) better in hardware.